## Sheet1
2017
Project Name - Timeline |  |  |  | March |  |  |  |  | April |  |  |  | May
Deliverables |  |  | Duration | W1 | W2 | W3 | W4 | w5 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w5
GUI Drafts (3/7) |  |  | 5 d | bar: March W1
Write down all forms needed in project | Task I | owner | .5 d | bar: March W1
Sketch out template for the project | Task II | owner | 1 d | bar: March W1
Include Data Fields | Task III | owner | .5 d | bar: March W1
Write out page map | Task IV | owner | .5 d | bar: March W1
Data Bases (3/14) |  |  | .5 d
Import Data | Task I | owner | .1d | bar: March W2
Determine correct data types for all fields | Task II | owner | .1d | bar: March W2
Add any new fields you think you may use | Task III | owner | .1d | bar: March W2
Set table primary keys | Task IV | owner | .1d | bar: March W2
Create the needed relationships with referential integrity enforced - refer to the provided database model (under the Course Project Module) for assistance. | Task V | owner | .1d | bar: March W2
Login Form (3/21) |  |  | 1w
Display user name and password to login | Task I | owner | .5d | bar: March W3
Log in successful for employee and member | Task II | owner | .5d | bar: March W3
Distinguish the accessibility between employee and member | bar: March W3
Member Account Forms (4/6) |  |  | 1w | bar: May w1 to May w5
Display member's account information | Task I | owner | .5d | bar: March W4 to May w5
Return/Renew Button for resources currently checked-out | Task II | owner | .5d | bar: March W4 to May w5
POP (04/13) |  |  | 1w
Member Employee and Search Forms (4/20) |  |  | 1w
Display search fields options(title and author's last name) | Task I | owner | 2d
Add navigation buttons on the search fields | Task II | owner | 2w
Display seached items for members | Task III | owner | 2d | bar: April w2
New Resource Forms (4/27) |  |  | 1w
Correct documentation and user instructions | Task I | owner | 1d | bar: April w3
Button functionalities | Task II | owner | 1d | bar: April w3
Search field database connections | Task III | owner | 1d | bar: April w3
Display available/unavailable seached items for employees | Task IV | owner | 1d | bar: April w3
Registration Form (5/4) |  |  | 1w
Register button inserts a record into LibraryMember Table | Task I | owner | 1d | bar: April w4
Cancel/clear navigation buttons | Task II | owner | 3d | bar: April w4
Error checking should be included for all required fields | Task III | owner | 3d | bar: April w4
Project Complete (5/4) |  |  | 1w
Correct overall look and asthetic | Task I | owner | 3d | bar: March W1 to May w1
Test with users | Task II | owner | 3d | bar: March W1 to May w1
Go down checklist | Task III | owner | 1d | bar: March W1 to May w1